## Stories
ID | Demo step | Story | Acceptance criteria | Baseline SP | Model | Effort | Multiplier | Adjusted SP | Status | Accepted (Y/N) | Actual runtime (min) | Raw actual SP | Normalised actual SP | Variance
S1 | all | Project scaffold in the fork: Node 22 TS package, npm scripts (`start`, `agent`, `reset`, `drop`, `compare`, `test`), `.env.example`, `.gitignore` for `.env` and `secrets/`, CI running unit tests, `appa describe --check` and `appa replay policy-tests/` | `npm test` passes on a fresh clone; CI is green on the first PR; `git check-ignore .env secrets/x` matches both; no secret in the repo | 2 | Opus 5.5 | medium |  |  | Done | Y
S2 | inputs, 1, 3 | Write the 11 synthetic seed files listed in the demo script | All 11 exist with the demo-script names; each starts with SPECIMEN; only 08 and 09 match `SPC-\d{4}-\d{4}`; 01 contains `Matter Ref: LM-2026-0417`; all names are fictional | 1 | Sonnet 5.5 | medium |  |  | Done | Y
S3 | setup, 0, 1, 3 | Drive client: list root, read, move, upload, trash, ensure subfolders. Auth is chosen by one `GDRIVE_AUTH` line (oauth, TBD, or service-account). Setup steps go in the README | `npm run drive:check` lists the root and creates any missing subfolder; switching `GDRIVE_AUTH` needs no code change; the OAuth token is cached under `secrets/`; refuses to run if `GDRIVE_ROOT_FOLDER_ID` is unset | 3 | Opus 5.5 | medium |  |  | Done | Y
S4 | 0 | `npm run reset`: trash everything under the test folder, upload seed 01–10 to the root, archive `logs/` to `runs/<stamp>/`, clear the outbox, memory and poller state | Step 0 "See" holds; running reset twice in a row gives the same state; it touches nothing outside `GDRIVE_ROOT_FOLDER_ID` (unit test with a fake Drive) | 1 | Opus 5.5 | medium |  |  | Done | Y
S5 | 1, 3 | Classifier: ID rule, then Jev `choice()` over {Legal, Accounting}, then the threshold; fixture replay or record-on-miss keyed by sha256(content) | With the committed fixture and no API key, unit tests give the demo-script label and rule for all 11 files; a miss is logged `"source":"live"`; the threshold comes from `.env` | 3 | Opus 5.5 | medium |  |  | Done | Y
S6 | 1, 3 | Record the Jev fixture live for the 11 files and commit it (needs the TypeSafe key) | File 10 records < 0.70; the other non-ID files record ≥ 0.70 with the expected label. If not, edit the seed text and re-record; never hand-edit the fixture | 1 | Opus 5.5 | low |  |  | Done | Y
S7 | 1, 3 | Poller: every 10 s, classify new root files, move them, log `classify` lines; ignore subfolders | Step 1: 10 files moved within 30 s. Step 3: the new file moves within 30 s with no restart. A file already in a subfolder is never reclassified | 2 | Opus 5.5 | medium |  |  | Done | Y
S8 | 1–4 | Decision log writer (shared JSONL), plus `npm run compare` over two run folders, plus a check against `expected-decisions.json` built from this script | Lines match the demo-script shapes; `compare` ignores timestamps and Drive IDs and sorts `classify` lines by file; it prints `identical`, or the first differing line and exits 1 | 1 | Sonnet 5.5 | medium |  |  | Done | Y
S9 | 1, 2a–2d | `appa.toml`: folder-labelled read tools, `send` with `contains = ["$to"]`, the `internal` list stub, memory save/load with scoped audiences, High Risk read denied. Plus `policy-tests/*.appa` | `appa describe --check` passes; `appa replay` passes files for 2a (deny), 2b (deny), 2c across two sessions (deny), 2d (allow) and a High Risk read (deny) | 3 | Opus 5.5 | high |  |  | Done | Y
S10 | 2a–2d | Sidecar and TS hook client: `npm start` launches `appa runtime`; every tool call is checked before it runs; a deny returns the short reason, rewritten from runtime text plus the session's label source (file or memory) | The exact 2a/2b/2c reason strings from the demo script are returned and logged; a denied call never runs its tool; unit tests use recorded runtime responses | 3 | Opus 5.5 | high |  |  | Done | Y
S11 | 2 | Tools: Drive read (returns content and folder label), mock `send` (appends to `logs/outbox.jsonl`), memory save/load (local JSON keyed by scope) | Each tool works alone in unit tests; `send` writes exactly one line per allowed call and none per denied call | 2 | Opus 5.5 | medium |  |  | Done | Y
S12 | 2 | Scripted agent: takes the task text, runs agent-1 (read Legal, 2a, 2b, memory save), then agent-2 (memory load, send), then agent-1 2d; prints each result | Step 2 "See" holds end to end against the live sidecar; outbox ends with exactly the 2d line; session IDs are fixed as `agent-1` and `agent-2` | 2 | Opus 5.5 | medium |  |  | Done | Y
Total
Baseline SP is the product agent's story estimate (Phase 1). Variance = normalised actual SP − baseline SP; positive means the story took longer than estimated. Task-level estimates (Phase 2) are compared on the Summary tab.

## Tasks
ID | Story ID | Task | Owner agent | Wave | Branch | Files owned | Dependencies | Baseline SP | Model | Effort | Multiplier | Adjusted SP | Start | End | Runtime (min) | Attempts | PR link | Accepted (Y/N) | Raw actual SP | Normalised actual SP | Notes
T1.1 | S1 | Node 22 TS package in `clearance/` with all npm scripts, stub CLIs, config loader, JSONL util, log schema and ignore rules. | Rowan | 1 | feat/T1.1-node-scaffold | `clearance/package.json`, `clearance/package-lock.json`, `clearance/tsconfig.json`, `clearance/vitest.config.ts`, `clearance/.env.example`, `clearance/README.md`, `clearance/src/config.ts`, `clearance/src/util/jsonl.ts`, `clearance/src/log/schema.ts`, `clearance/src/cli/{start,agent,reset,drop,compare,drive-check,record-fixture}.ts` (stubs), `clearance/test/config.test.ts`, `clearance/test/jsonl.test.ts`, `.gitignore`. | none | 2 | Opus 5.5 | medium |  |  | 2026-10-19 12:28 | 2026-10-19 12:34 |  | 1 | https://github.com/soham956/OpenAPPA/pull/4 | Y |  |  | Accepted. Combined wave-1 check: vitest 30/30, typecheck ok, policy 8/8.
T2.1 | S2 | Write the 11 synthetic SPECIMEN seed files. | Mika | 1 | feat/T2.1-seed-files | `clearance/seed/01-…10-*.txt`, `clearance/seed/new/11-vendor-invoice-0207.txt`, `clearance/test/seed.test.ts`. | none | 1 | Sonnet 5.5 | medium |  |  | 2026-10-19 12:35 | 2026-10-19 12:36 |  | 2 | https://github.com/soham956/OpenAPPA/pull/2 | Y |  |  | Accepted after rework (attempt 2). Runtime includes the rejected attempt row.
T9.1 | S9 | Policy and policy tests. First, spike array recipients (`@rcpt:addr/$to` with the node identity source) and switch to the documented fallback if it fails. | Quinn | 1 | feat/T9.1-appa-policy | `clearance/appa.toml`, `clearance/policy/rcpt-audience.mjs`, `clearance/policy/README.md`, `clearance/policy-tests/*.appa`. | none (needs P1) | 3 | Opus 5.5 | high |  |  | 2026-10-19 12:28 | 2026-10-19 12:33 |  | 1 | https://github.com/soham956/OpenAPPA/pull/3 | Y |  |  | Accepted. Spike: array recipients via @rcpt:addr/$to work (no fallback). describe --check exit 0, replay 8/8 (orchestrator rerun).
T1.2 | S1 | One CI workflow. Delete the upstream workflows, build `appa` with caching, and run the tests and policy checks. | Rowan | 2 | feat/T1.2-ci | `.github/workflows/clearance-ci.yml`. Deletes the 13 upstream `.github/workflows/*.yml` files and `.github/dependabot.yml`. | T1.1, T9.1 | 2 | Opus 5.5 | medium |  |  | 2026-10-19 13:15 | 2026-10-19 13:21 |  | 1 | https://github.com/soham956/OpenAPPA/pull/11 | Y |  |  | Accepted: CI green cold (4m31s) and cached (19s, cache hit); check clearance-ci now required on main. Blocked 9.7 min waiting for Soham's workflow scope: wall-clock End-Start includes that; active time 8.1 min.
T3.1 | S3 | `DriveClient` interface, the googleapis implementation and an in-memory fake. | Sasha | 2 | feat/T3.1-drive-client | `clearance/src/drive/{types,google,fake}.ts`, `clearance/test/drive-google.test.ts`, `clearance/test/drive-contract.test.ts`. | T1.1 | 2 | Opus 5.5 | medium |  |  | 2026-10-19 13:04 | 2026-10-19 13:08 |  | 1 | https://github.com/soham956/OpenAPPA/pull/9 | Y |  |  | Accepted: in scope (5 files), contract suite runs on fake and Google stub, trash is soft (trashed=true), DriveScopeError outside the tree. Combined wave-2 check passed (128/128).
T5.1 | S5 | ID rule, threshold decision and fixture store (replay, or record on a miss) keyed by sha256(content). | Ellis | 2 | feat/T5.1-classifier-core | `clearance/src/classifier/{types,specimen,decide,fixture-store}.ts`, `clearance/test/classifier.test.ts`, `clearance/test/fixtures/classifications.sample.json`. | T1.1, T2.1 | 2 | Opus 5.5 | medium |  |  | 2026-10-19 13:44 | 2026-10-19 13:46 |  | 2 | https://github.com/soham956/OpenAPPA/pull/8 + #23 (rework) | Y |  |  | Accepted after rework (PR #23): fixture built from seed files at test time, no writes to committed files. Original PR #8 work counted as the rejected attempt row.
T8.1 | S8 | Decision log writer and reader on top of `schema.ts`. | Mika | 2 | feat/T8.1-decision-log | `clearance/src/log/decision-log.ts`, `clearance/test/decision-log.test.ts`. | T1.1 | 1 | Sonnet 5.5 | medium |  |  | 2026-10-19 13:03 | 2026-10-19 13:04 |  | 1 | https://github.com/soham956/OpenAPPA/pull/6 | Y |  |  | Accepted: in scope (2 files), exact-string tests of demo-script lines; combined wave-2 check passed (128/128).
T10.1 | S10 | Sidecar launcher, typed `/hook` client and remedy executor over MCP. | Quinn | 2 | feat/T10.1-sidecar-wire | `clearance/src/sidecar/{runtime,wire,remedy}.ts`, `clearance/test/sidecar-wire.test.ts`, `clearance/test/sidecar-live.test.ts`, `clearance/test/fixtures/runtime/*.json`. | T1.1, T9.1 | 3 | Opus 5.5 | high |  |  | 2026-10-19 13:03 | 2026-10-19 13:10 |  | 1 | https://github.com/soham956/OpenAPPA/pull/10 | Y |  |  | Accepted: live remedy flow against real appa; combined wave-2 check 128/128 incl. live, typecheck ok, policy 8/8. Live feedback wording differs from replay (T10.2 must use recorded fixtures).
T11.1 | S11 | Mock `send` (outbox) and the memory save/load tools. | Remy | 2 | feat/T11.1-send-memory-tools | `clearance/src/tools/{send,memory}.ts`, `clearance/test/tools-send.test.ts`, `clearance/test/tools-memory.test.ts`. | T1.1 | 1 | Sonnet 5.5 | medium |  |  | 2026-10-19 13:04 | 2026-10-19 13:06 |  | 1 | https://github.com/soham956/OpenAPPA/pull/7 | Y |  |  | Accepted: in scope (4 files), no APPA calls, outbox written via schema orderKeys; combined wave-2 check passed (128/128). PR body end time 13:06:00Z is slightly off; real end used.
T3.2 | S3 | `GDRIVE_AUTH` switch (oauth or service-account), OAuth loopback consent with a token cache, factory, `npm run drive:check`, setup doc. | Sasha | 3 | feat/T3.2-drive-auth | `clearance/src/drive/{auth,factory}.ts`, `clearance/src/cli/drive-check.ts`, `clearance/docs/drive-setup.md`, `clearance/test/drive-auth.test.ts`. | T1.1, T3.1 | 2 | Opus 5.5 | medium |  |  | 2026-10-19 13:30 | 2026-10-19 13:34 |  | 1 | https://github.com/soham956/OpenAPPA/pull/19 | Y |  |  | Accepted: CI green, 16 tests with stubs, PKCE loopback consent (127.0.0.1), token mode 600, no live run. Combined wave-3 check 220/220.
T4.1 | S4 | `npm run reset` and `npm run drop`. | Rowan | 3 | feat/T4.1-reset-drop | `clearance/src/reset/reset.ts`, `clearance/src/cli/{reset,drop}.ts`, `clearance/test/reset.test.ts`. | T1.1, T3.1 | 1 | Opus 5.5 | medium |  |  | 2026-10-19 13:30 | 2026-10-19 13:33 |  | 1 | https://github.com/soham956/OpenAPPA/pull/17 | Y |  |  | Accepted: in scope, CI green, 13 tests on fake incl. outsideTreeIds()=[] and sidecar refusal. Real Drive factory not yet wired (TODO(T3.2) seam) - wiring scheduled for wave 4. Combined wave-3 check 220/220.
T5.2 | S5 | TypeSafe `choice()` adapter and the `npm run fixture:record` CLI. | Ellis | 3 | feat/T5.2-jev-adapter | `clearance/src/classifier/jev.ts`, `clearance/src/cli/record-fixture.ts`, `clearance/test/jev.test.ts`. | T5.1 | 1 | Opus 5.5 | medium |  |  | 2026-10-19 13:30 | 2026-10-19 13:33 |  | 1 | https://github.com/soham956/OpenAPPA/pull/18 | Y |  |  | Accepted: CI green, each commit builds, SDK mocked, content-only. Orchestrator ruling: fixture holds 9 entries (08/09 never reach Jev - ID rule first); demo-script wording to be corrected.
T7.1 | S7 | Root poller: classify, move, log. | Jules | 3 | feat/T7.1-poller | `clearance/src/poller/poller.ts`, `clearance/test/poller.test.ts`. | T3.1, T5.1, T8.1 | 2 | Opus 5.5 | medium |  |  | 2026-10-19 13:30 | 2026-10-19 13:32 |  | 1 | https://github.com/soham956/OpenAPPA/pull/16 | Y |  |  | Accepted: in scope (2 files), CI green, 9 tests incl. restart/retry. Known edge: a log-write failure after a successful move loses that classify line (noted for T7.2). Combined wave-3 check 220/220.
T8.2 | S8 | `npm run compare` and `expected-decisions.json`. | Mika | 3 | feat/T8.2-compare | `clearance/src/log/compare.ts`, `clearance/src/cli/compare.ts`, `clearance/expected-decisions.json`, `clearance/test/compare.test.ts`. | T8.1, T2.1 | 1 | Sonnet 5.5 | medium |  |  | 2026-10-19 13:30 | 2026-10-19 13:33 |  | 1 | https://github.com/soham956/OpenAPPA/pull/15 | Y |  |  | Accepted: in scope (4 files), CI green, 18 tests; reasons checked against demo-script text. Combined wave-3 check 220/220.
T10.2 | S10 | The guard: sessions, trusted args, narrowing acceptance, tool run and `tool_result`, reason rewrite, `enforce` lines. | Quinn | 3 | feat/T10.2-guard | `clearance/src/sidecar/{guard,reasons,audiences}.ts`, `clearance/test/guard.test.ts`, `clearance/test/reasons.test.ts`, `clearance/test/fixtures/runtime/guard/*.json`. | T10.1, T8.1, T9.1, T11.1, T3.1 | 3 | Opus 5.5 | high |  |  | 2026-10-19 13:30 | 2026-10-19 13:37 |  | 1 | https://github.com/soham956/OpenAPPA/pull/20 | Y |  |  | Accepted: exact 2a/2b/2c reasons live + replayed from fixtures; denied tools never run; CI ran live guard tests. Combined wave-3 check 220/220. Has its own default drive tools - T12.1 to inject T11.2's.
T11.2 | S11 | `drive_list` and `drive_read` tools. | Remy | 3 | feat/T11.2-drive-tools | `clearance/src/tools/drive.ts`, `clearance/test/tools-drive.test.ts`. | T3.1 | 1 | Sonnet 5.5 | medium |  |  | 2026-10-19 13:30 | 2026-10-19 13:32 |  | 1 | https://github.com/soham956/OpenAPPA/pull/14 | Y |  |  | Accepted: in scope (2 files), CI green, no APPA calls, DriveScopeError outside tree. Combined wave-3 check 220/220.
T3.3 | S3 | Live Drive check against the real folder. Fix any Workspace or Shared Drive quirks. | Sasha | 4 | feat/T3.3-live-drive | `clearance/src/drive/{google,auth}.ts`, `clearance/docs/drive-setup.md`. | T3.2, T4.1 | 1 | Opus 5.5 | medium |  |  | 2026-10-19 13:49 | 2026-10-19 13:52 |  | 1 | (no PR - verification only, no fixes needed) | Y |  |  | Accepted: live drive:check without browser, reset x3 + drop on real Workspace Drive, step 0 state verified, no fixes. Reset ~23-45s (don't run live mid-demo). Consent click done by Soham (not agent time). Orchestrator verified git status clean.
T6.1 | S6 | Record the Jev fixture live for all 11 files, commit it, and add the full-fixture classifier test. | Noor | 4 | feat/T6.1-record-fixture | `clearance/fixtures/classifications.json`, `clearance/test/classifier-fixture.test.ts`. It may edit `clearance/seed/10-settlement-payment-schedule.txt` only to re-record. | T5.2, T2.1 | 1 | Opus 5.5 | low |  |  | 2026-10-19 13:46 | 2026-10-19 13:48 |  | 1 | https://github.com/soham956/OpenAPPA/pull/25 | Y |  |  | Accepted: 9-entry fixture (01-07,11 at 1.0; 10 Legal 0.66 -> low-confidence), 3 live runs, seed 10 edited, no secrets, CI green. Paused while T5.1 test fix landed (not Noor's defect).
T7.2 | S7 | `npm start`: start the sidecar, then the poller. Ctrl-C stops both. | Remy | 4 | feat/T7.2-start | `clearance/src/cli/start.ts`, `clearance/test/start.test.ts`. | T7.1, T10.1, T3.2 | 1 | Sonnet 5.5 | medium |  |  | 2026-10-19 13:40 | 2026-10-19 13:43 |  | 1 | https://github.com/soham956/OpenAPPA/pull/22 | Y |  |  | Accepted: CI green, 8 tests (order, signals, sidecar death, fail-fast before sidecar). Combined wave-4 check pending.
T12.1 | S12 | The scripted agent and `npm run agent`. | Rowan | 4 | feat/T12.1-scripted-agent | `clearance/src/agent/script.ts`, `clearance/src/cli/agent.ts`, `clearance/test/agent.test.ts`. | T10.2, T11.1, T11.2, T3.2 | 2 | Opus 5.5 | medium |  |  | 2026-10-19 13:47 | 2026-10-19 13:50 |  | 2 | https://github.com/soham956/OpenAPPA/pull/24 | Y |  |  | Accepted attempt 2: guarded drive_list under new 'list' step (schema.ts STEPS), 7 tests, CI green, merged #24. Real-runtime check conforms once guard logs caller's step (Quinn follow-up) and #26 lands.
T12.2 | S12 | CI end-to-end test of step 2 with the real `appa` sidecar and a fake Drive. | Rowan | 5 | feat/T12.2-e2e-step2 | `clearance/test/e2e/step2.test.ts`, `clearance/test/e2e/helpers.ts`. | T12.1, T8.2 | 2 | Opus 5.5 | medium |  |  | 2026-10-19 13:54 | 2026-10-19 13:56 |  | 1 | https://github.com/soham956/OpenAPPA/pull/29 | Y |  |  | Accepted: e2e step 2 against real appa + fake Drive, conforms to expected (11 enforce + 1 outbox), second run identical, ran in CI (not skipped).
T2.1 | S2 |  | Mika | 1 |  |  |  |  | Sonnet 5.5 | medium |  |  | 2026-10-19 12:28 | 2026-10-19 12:30 |  |  |  | N |  |  | Rejected attempt 1: tsc TS2345 at seed.test.ts:50 (only visible once T1.1's TypeScript was applied).
T5.1 | S5 |  | Ellis | 2 |  |  |  |  | Opus 5.5 | medium |  |  | 2026-10-19 13:04 | 2026-10-19 13:07 |  |  |  | N |  |  | Original attempt: later found defective (sample fixture keyed to seed-10 hash; tests wrote into committed fixture) - superseded by rework.
T1.2 | S1 |  | Rowan | 2 |  |  |  |  | Opus 5.5 | medium |  |  | 2026-10-19 13:03 | 2026-10-19 13:05 | [6 empty] | Earlier work segment of the accepted attempt (paused while blocked).
T8.2 | S8 |  | Mika | 3 |  |  |  |  | Sonnet 5.5 | medium |  |  | 2026-10-19 13:47 | 2026-10-19 13:48 |  |  | https://github.com/soham956/OpenAPPA/pull/26 |  |  |  | Follow-up (orchestrator request, not rework): expected list line for guarded drive_list (PR #26, merges after #24)
T4.1 | S4 |  | Rowan | 3 |  |  |  |  | Opus 5.5 | medium |  |  | 2026-10-19 13:40 | 2026-10-19 13:43 |  |  | https://github.com/soham956/OpenAPPA/pull/21 |  |  |  | Follow-up (orchestrator request, not rework): wire Drive factory into reset/drop (PR #21)
T10.2 | S10 |  | Quinn | 3 |  |  |  |  | Opus 5.5 | high |  |  | 2026-10-19 13:51 | 2026-10-19 13:53 |  |  | https://github.com/soham956/OpenAPPA/pull/27 |  |  |  | Follow-up (orchestrator request, not rework): guard logs caller's step for drive_list (PR #27)
T6.1 | S6 |  | Noor | 4 |  |  |  |  | Opus 5.5 | low |  |  | 2026-10-19 13:41 | 2026-10-19 13:43 | [6 empty] | Earlier work segment of the accepted attempt (paused while blocked).
T12.1 | S12 |  | Rowan | 4 |  |  |  |  | Opus 5.5 | medium |  |  | 2026-10-19 13:43 | 2026-10-19 13:46 |  |  |  | N |  |  | Rejected attempt 1: agent discovered Legal files via unguarded DriveClient.list to fit expected file; orchestrator requires guarded drive_list under new 'list' step.
Note on N1: Implementer's logged start time (local). Fill in.

## Agents
Agent | Model | Effort | Multiplier | Lane | Tasks assigned | Tasks accepted | Rejected attempts | Baseline SP | Adjusted SP | Runtime (min) | Raw actual SP | Normalised actual SP | Actual ÷ estimate (raw ÷ adjusted, accepted)
Quinn | Opus 5.5 | high |  | Policy and sidecar
Rowan | Opus 5.5 | medium |  | Platform: scaffold, CI, reset, agent, e2e
Sasha | Opus 5.5 | medium |  | Drive
Ellis | Opus 5.5 | medium |  | Classifier
Jules | Opus 5.5 | medium |  | Poller
Mika | Sonnet 5.5 | medium |  | Seed data and decision log
Remy | Sonnet 5.5 | medium |  | Tools and npm start
Noor | Opus 5.5 | low |  | Fixture recording
Total
Each agent is one persistent worker with a fixed model and effort; it keeps its lane across waves and is continued, not restarted, for its next task. Every Tasks row (including rejected attempts) names its agent in Owner agent.

## Calibration
Calibration: model and effort multipliers
Adjusted SP = baseline SP × multiplier. Raw actual SP = runtime minutes ÷ 20. Normalised actual SP = raw ÷ multiplier. Ratio > 1 means that model/effort ran slower than estimated; the implied multiplier is what the data so far suggests.
Key | Model | Effort | Multiplier | Reasoning | Accepted tasks | Baseline SP (accepted) | Adjusted SP (accepted) | Raw actual SP | Actual ÷ estimate (raw ÷ adjusted) | Implied multiplier (raw ÷ baseline)
| Opus 5.5 | medium | 1 | Baseline by definition: 1 SP = up to 20 min of Opus 5.5 at medium effort.
| Opus 5.5 | high | 1.2 | Fixed by Soham. More deliberation per step: roughly +20% runtime for the same task.
| Opus 5.5 | low | 0.85 | Brief's starting point. Less thinking per step, but tool calls and test runs don't shrink, so the saving (-15%) is smaller than the high premium (+20%).
| Opus 5.5 | xhigh | 1.45 | Brief's starting point. Roughly one more high-sized step above high (+25% on top of 1.2), as thinking budgets grow faster at the top end.
| Opus 5.5 | max | 1.75 | Extrapolated: another step of about +0.3 above xhigh. Not used in this plan.
| Sonnet 5.5 | medium | 0.7 | Brief's starting point for a smaller model at medium. Faster output, partly offset by more retries on edge cases. Used only for simple, well-specified tasks.
| Haiku 5.5 | medium | 0.55 | Extrapolated below Sonnet. Not used in this plan.
Note on D6: Fixed rule from Soham (brief).

## Summary
Summary: estimated vs actual SP
How to use: fill in only the yellow cells on Tasks (Start, End, Attempts, PR link, Accepted, Notes) and on Stories (Status, Accepted). Log a rejected attempt on its own Tasks row: same ID, Story ID, Wave, Owner agent, Model and Effort, blank Baseline SP, Accepted = N, and the reason in Notes. Blue = typed-in value, black = formula, green = link to another tab.
By story
Story | Story estimate SP (Phase 1) | Task baseline SP (Phase 2) | Task adjusted SP | Raw actual SP | Normalised actual SP | Variance vs task baseline | Accepted
Total
By wave
Wave | Tasks | Baseline SP | Adjusted SP | Raw actual SP | Normalised actual SP | Variance vs baseline | Tasks accepted
1
2
3
4
5
Total
Planning phases (actuals only; not estimated, not in the totals above)
Phase | Agent | Model / effort | Runtime (min) | Raw actual SP | Accepted | Source
Phase 1 | Product agent | Opus 5.5 high | 3.86 |  | Y | Sub-agent duration reported by Claude Code, 2026-10-19
Phase 2 | Dev lead agent | Opus 5.5 high | 11.56 |  | Y | Sub-agent duration reported by Claude Code, 2026-10-19
Later list (out of POC scope)
Per-value taint, so external sends of unrelated values after a Legal read are allowed.
Per-record memory labels, instead of scoped audiences.
An LLM-driven agent instead of the scripted one.
A release workflow or UI for the review hold, beyond moving the file in Drive.
Real ID detectors (SSN, passport and so on) beyond the SPECIMEN format.
Google Docs, PDF and OCR input.
Per-team audiences (an Accounting list separate from `internal`).
Copies and summaries carrying the source clearance, and sanitizers or redaction.
Real email.
Drive webhooks.
Reclassifying a file when it is edited.
Hashirai Registry integration.
A decision-log viewer.
Retries, rate limits and deployment.
Poller durability: if the log write fails after a successful move, that classify line is lost. Persist pending lines and retry them.
A wider confidence margin for seed 10. It records at 0.66 against the 0.70 threshold, so a live re-record could cross it.
A faster reset on Workspace Drive (batch calls); today it takes 23–45 s.